GovIQ — Design Team Review

57 Rathbeale Road — CRC Omni Unit 48A

Sprint Plan — Full Multi-Disciplinary Design Review

# 1. Sprint context

This sprint runs a full multi-disciplinary design review on the CRC Omni Unit 48A tender pack at 57 Rathbeale Road, ahead of the 10-Jun-2026 cut-off. The driver is a solo orchestrator running 10 chartered AI review skills against the pack, with stakeholder validation only on CRITICAL and HIGH findings.

The standing position from the working discrepancy register is: 3 CRITICAL items (party-identity ambiguity, BCAR/PW-CF5 mismatch, blank Substantial Completion date) that must be resolved before issue, 18 HIGH items requiring drafted corrections, 24 MEDIUM and 15+ LOW items for inclusion in the master register. Variation exposure if all CRITICAL/HIGH go unresolved at award sits in the €24k–€270k band (5–25% of likely Contract Sum).

The plan compresses the work into 10 working days with the Irish June Bank Holiday excluded. Each day has a hard exit gate. No phase carries more than one day of slack. The sprint exits when the RFI register / revised pack is submitted with timestamped evidence before 17:00 on 10-Jun-2026.

# 2. Sprint metadata

| Sprint window | Wed 27-May-2026 → Wed 10-Jun-2026 (15 calendar days) |
| --- | --- |
| Working days | 10 (Irish June Bank Holiday Mon 1-Jun-2026 excluded) |
| Hard gate | Tender pack issue / RFI cut-off — Wed 10-Jun-2026, 17:00 |
| Driver | Solo orchestrator (Liam) + 10 AI review skills |
| Scope | 10-skill findings register · 30-item RFI register · 14-item pre-contract checklist · Variation exposure quantification · Pre-issue tender pack cleanup |
| Standing brief | Convert every discrepancy that materially affects compliance, cost certainty, programme or contract enforceability into a logged finding with a recommended action before tender issue. |
| Owner / Approver | Liam Dunne (orchestrator) · CA / Employer (approver) · ER (counter-signer) |
| Document version | v1.0 — 27-May-2026 |

# 3. Day-0 scope ambiguity — resolve in Day-1 Activity 1

Direction of the RFI register — must be confirmed before any review work proceeds The project brief describes the 30-item register as 'RFIs addressed to the CA before the 10-06-2026 query cut-off' (bidder-side framing — pack is already issued, sprint produces formal RFIs to the CA). The user scope statement says 'issues that require changing before we issue the tender documentation' (Employer-side framing — pack not yet issued, sprint produces internal change requests for pre-issue correction). These imply different submission mechanics, different recipients, different legal weight, and different document control. The wrong assumption invalidates the RFI register format. Default working assumption: Employer-side / pre-issue (consistent with chartered design-team skill set and the pre-contract action checklist scope). Confirm in writing with CA / Employer in Day-1 Activity 1. If wrong, switch submission route — register content is unaffected.

# 4. Phase overview

| Phase | Days | Focus | Exit gate |
| --- | --- | --- | --- |
| P1 | Day 1–2 · 27–28 May | Intake, manifest, CRITICAL lockdown | All 3 CRITICAL items ratified + escalation path open |
| P2 | Day 3–7 · 29 May / 2–5 Jun | 10-skill discipline reviews + variation costing | Consolidated discrepancy register v1 with severity-tagged findings |
| P3 | Day 8–10 · 8–10 Jun | Stakeholder cycle, QA, RFI submission / pack issue | Submitted / issued before 17:00 on 10-Jun-2026 |

# 5. Day-by-day plan

### Day 1 — Wed 27-May-2026 · Sprint kickoff & tender pack intake

Focus: Lock the scope ambiguity, build the manifest, instantiate the findings store.

Activities:

- Resolve direction-of-RFI ambiguity (pre-issue internal change register vs post-issue RFIs to CA). Confirm in writing with CA / Employer.

- Inventory the full tender pack: drawings, specs, BoQ, FOT, ITT, FTS, BCAR Ancillary Cert list, M&E pricing, structural calcs.

- Stand up findings register (Convex schema matching the 10 chartered skills) — fields locked to: severity, category, document, section, regulatory_basis, operational_risk, recommended_action, evidence_quote.

- Run initial triage scan on TOC and document hygiene (cross-reference broken links, missing appendices, naming convention drift).

| Skills run | arch-review-ireland (TOC sweep only) · contract-admin-pwcf-ireland (party identity check) |
| --- | --- |
| Inputs | Full tender pack (PDF/DWG/XLSX), Project Brief, Employer correspondence |
| Outputs | Pack manifest · Findings store schema live · Day-1 triage register · Confirmation of RFI direction |
| Exit gate | Manifest complete · RFI direction confirmed · CRITICAL items C-01, C-02, C-03 queued for Day-2 deep-dive |
| Day risk | If pack manifest reveals missing documents (e.g. FSC, DAC, F-Gas declarations), Day-2 capacity is consumed chasing rather than reviewing. |

### Day 2 — Thu 28-May-2026 · CRITICAL lockdown

Focus: Ratify the 3 CRITICAL findings with regulatory basis and contract impact. These are stop-the-issue items.

Activities:

- C-01 Employer / CA / Building Owner identity — cross-check across FTS Notice, ITT, FOT, Conditions of Contract, BCAR appointments. Confirm legal entity numbers (HSE/Section 38–39/CRC Children's Disability Network Team).

- C-02 BCAR document set written for D&B but contract is PW-CF5 Employer-Designed — produce side-by-side mapping of design responsibility per SI 9/2014, demonstrate the gap, draft revised BCAR Ancillary Cert scope.

- C-03 Date for Substantial Completion blank — derive defensible date from programme, quantify LD rate per day, draft replacement clause for Schedule Part 1 Clauses 1.1.16 & 11.

- For each CRITICAL: draft RFI / internal change request text, propose corrected wording, identify owner (Employer / ER / Designer).

| Skills run | arch-review-ireland · cs-review-ireland · contract-admin-pwcf-ireland · qs-review-cwmf-ireland |
| --- | --- |
| Inputs | Day-1 register · Tender pack · CWMF ARM4 + Supp1Iss2 · SI 9/2014 · PW-CF5 baseline |
| Outputs | 3 CRITICAL findings ratified with regulatory citation, contract impact, corrected text, owner |
| Exit gate | If any CRITICAL cannot be resolved by Day-2 EOD, escalate to CA same evening — these block tender issue. |
| Day risk | C-02 BCAR/PW-CF5 mismatch may require full BCAR re-issue with revised Ancillary Cert list — schedule risk extends beyond sprint window. |

### Day 3 — Fri 29-May-2026 · Architectural + Civil/Structural deep review

Focus: Full pass with arch + C&S skills against drawings, specs, calcs and BCAR pack.

Activities:

- arch-review-ireland: TGD B Vol 2 (2024) fire safety, TGD M Part M, BS 8300-2:2018 accessibility, BS 9991:2024 residential fire, NDA Building for Everyone, Changing Places Consortium, HBN/HTM, HIQA (Section 38–39 healthcare estates).

- cs-review-ireland: Eurocodes + Irish NAs, I.S. EN 13670 / 1090 / 206, TGD A/C/D/H, GDSDS, TII Spec, BCAR SI 9/2014 — focus on Ancillary Cert scope alignment.

- Cross-check Irish standard prefix errors (the known IS EN 10101 issue and similar across the pack).

- Reconcile contradictory car-park scope statements between architectural drawings and specification.

| Skills run | arch-review-ireland · cs-review-ireland |
| --- | --- |
| Inputs | Drawing register · Architectural spec · Structural calcs · BCAR pack · Ancillary Cert list |
| Outputs | Arch findings register · C&S findings register · Standards-citation correction log |
| Exit gate | Arch + C&S sub-registers severity-tagged and ready for merge |
| Day risk | Drawing-spec contradictions may multiply findings beyond initial estimate; cap output volume by deferring LOW items to post-issue addenda. |

### Day 4 — Tue 2-Jun-2026 · M&E pricing & specification reconciliation

Focus: Five mech skills run as parallel batch against M&E pricing docs, plant schedules, and brand specifications.

Activities:

- Resolve hoist brand conflict (CARBITAN vs ARJO vs SEA) — determine governing specification, draft single-source clarification.

- Verify M&E pricing references against project address (known wrong-project-address finding in pricing docs).

- F-Gas check under EU 2024/573 for any refrigerant-bearing plant.

- Cause-and-effect matrix gap analysis — flag as required deliverable for tenderers.

- DAC / FSC status confirmation per discipline.

| Skills run | 5x mech-review-*-ireland (HVAC, plumbing/drainage, BMS/controls, fire/life-safety, medical-gas if applicable) running in parallel batch |
| --- | --- |
| Inputs | M&E spec · M&E BoQ / pricing · Plant schedule · Manufacturer datasheets · F-Gas register (if extant) |
| Outputs | Consolidated M&E findings register · Hoist resolution path · Cause-and-effect matrix scope brief |
| Exit gate | Single-source-of-truth hoist spec agreed (or escalated) |
| Day risk | Manufacturer brand conflict may require client commercial decision (procurement preference vs clinical preference); flag for CA same day. |

### Day 5 — Wed 3-Jun-2026 · Electrical + life-safety review

Focus: Full pass with ee-review against electrical pack, disabled-alarm provisions, HTM/HBN compliance.

Activities:

- I.S. 10101:2020 electrical compliance.

- I.S. 3217:2023 emergency lighting · I.S. 3218:2024 fire detection.

- BS 8300-2 §18.6 disabled-refuge alarm and accessible WC alarm provisions — confirm cause-and-effect linkage.

- HTM 06-01 / 06-02 / 08-03 healthcare electrical resilience.

- CIBSE LG7 (offices) / LG10 (daylight) lighting design — applicable zones only.

| Skills run | ee-review-ireland |
| --- | --- |
| Inputs | Electrical spec · Single-line diagrams · Lighting schedule · Fire-alarm cause-and-effect (if extant) · BMS interface schedule |
| Outputs | EE findings register · Disabled-alarm gap log · Standards compliance summary |
| Exit gate | EE register merged into master discrepancy register |
| Day risk | Cause-and-effect matrix may be absent across multiple disciplines — convert to RFI to tenderers requiring submission with bid. |

### Day 6 — Thu 4-Jun-2026 · QS / CWMF commercial review + variation exposure

Focus: Run qs-review-cwmf against the FTS / ITT / MF stack and quantify €24k–€270k variation exposure per finding.

Activities:

- ARM4 + Supp1Iss2 alignment — confirm pricing document structure, BoQ measurement consistency under CESMM4 Revised / TII RMP.

- ITT date-arithmetic check (known finding) — calendar-day vs working-day errors, standstill period correctness under SI 284/2016.

- FOT Schedule Part 1 blank-fields audit — populate or flag every empty contractual field.

- Clause 15 Price Variation mechanics — confirm indices, application thresholds, sample calculation.

- Variation exposure quantification — apply €/% bands to each CRITICAL and HIGH finding to produce live exposure model (€24k–€270k range tested against current findings).

- CE-17 administrative readiness check.

| Skills run | qs-review-cwmf-ireland |
| --- | --- |
| Inputs | FTS Notice · ITT · Form of Tender (Part 1/2) · MF · BoQ · CWMF guidance · SI 284/2016 |
| Outputs | QS findings register · Variation exposure model (live spreadsheet linked to findings) · FOT Schedule Part 1 redline |
| Exit gate | Variation exposure rolled up — total €-range published |
| Day risk | Variation exposure may exceed €270k upper bound if HIGH-tier findings cluster; flag for cost-report sign-off. |

### Day 7 — Fri 5-Jun-2026 · Contract admin lifecycle + consolidation

Focus: Close the contract-admin skill pass, then consolidate all 10 sub-registers into the master discrepancy register.

Activities:

- contract-admin-pwcf-ireland: PW-CF1/3/5 lifecycle alignment, LoA preconditions, Commencement Notice readiness, Construction Contracts Act 2013 payment provisions, standstill rules.

- Build the 14-item Pre-Contract Action Checklist (sequenced Employer → ER → Designers → Contractor) populated from all 10 sub-registers.

- Merge all 10 discipline sub-registers into single master register — deduplicate cross-discipline findings, assign unique IDs (A-, S-, M-, E-, Q-, C- prefixes).

- Map every finding to its RFI / internal change request — produce the 30-item RFI register draft.

- Run severity recount: confirm CRITICAL/HIGH/MEDIUM/LOW counts against working-document targets (3/18/24/15+).

| Skills run | contract-admin-pwcf-ireland |
| --- | --- |
| Inputs | All 10 sub-registers · PW-CF5 baseline · Construction Contracts Act 2013 · SI 284/2016 |
| Outputs | Master discrepancy register v1 · 30-item RFI register draft · 14-item Pre-Contract Action Checklist v1 · Severity counts |
| Exit gate | Master register frozen for Phase-3 stakeholder review |
| Day risk | Cross-discipline deduplication may collapse counts below working targets, or expansion may push above — surface variance to CA same day for expectation management. |

### Day 8 — Mon 8-Jun-2026 · Stakeholder review cycle — Employer / CA / ER

Focus: Push master register + RFI register + pre-contract checklist to Employer / CA / ER for response. Manage turnaround.

Activities:

- Issue review package: master discrepancy register, RFI register draft, 14-item pre-contract checklist, variation exposure model.

- Hold structured review session(s) — agenda mapped to CRITICAL → HIGH → MEDIUM → LOW.

- Capture stakeholder amendments, accept/reject decisions, ownership assignments.

- Log all responses to findings store with timestamp, author, decision.

- Identify items requiring contract amendment vs items resolvable by addenda vs items deferred to post-issue clarification.

| Skills run | (orchestration — no skill execution) |
| --- | --- |
| Inputs | Master register v1 · RFI register draft · Pre-contract checklist · Variation exposure model |
| Outputs | Stakeholder-marked register v1.1 · Decision log · Items requiring CA / Employer sign-off |
| Exit gate | Stakeholder responses captured for all CRITICAL + HIGH items by EOD |
| Day risk | Stakeholder latency is the single biggest schedule risk in Phase 3 — set 24h response SLA in cover note, escalation if breached. |

### Day 9 — Tue 9-Jun-2026 · Amendments, QA, final formatting

Focus: Incorporate stakeholder amendments, freeze final register, run QA on regulatory citations and document references.

Activities:

- Apply all accepted amendments to master register and RFI register.

- Re-run regulatory citation checker — confirm every reference resolves (no IS EN 10101-style errors).

- Cross-check every finding's document/section reference against current pack version.

- Format RFI register for eTenders submission (or revised tender pack issue manifest, depending on Day-1 RFI direction decision).

- Final variation exposure roll-up with stakeholder-confirmed valuations.

- Produce Sprint Output Pack: master register · RFI register · pre-contract checklist · variation model · CA cover note.

| Skills run | (QA / format — no skill execution) |
| --- | --- |
| Inputs | Stakeholder-marked register v1.1 · Final pack version |
| Outputs | Sprint Output Pack v2.0 — submission-ready |
| Exit gate | Output Pack QA-signed by Liam · CA pre-clearance received (if applicable) |
| Day risk | Late-breaking stakeholder amendments on Day 9 compress QA window — hold a hard 13:00 cut-off for amendment intake. |

### Day 10 — Wed 10-Jun-2026 · Submission / Issue day

Focus: Submit RFI register via eTenders OR issue revised tender pack via Employer's procurement route, before 17:00 cut-off.

Activities:

- Final pre-submission checklist (see Sprint Exit Checklist section).

- Submit RFI register to CA via eTenders before 17:00 (post-issue scenario) OR distribute revised tender pack to bidders via procurement route (pre-issue scenario).

- Distribute Sprint Output Pack v2.0 to: Employer, CA, ER, Lead Designer, QS.

- Confirm submission receipt / pack issue with evidence.

- Sprint retrospective (30 min) — capture lessons for next pack review.

- Archive working files; close sprint in tracker.

| Skills run | (submission orchestration) |
| --- | --- |
| Inputs | Sprint Output Pack v2.0 |
| Outputs | Confirmed submission / issue · Retro log · Sprint closed |
| Exit gate | Submission timestamp before 17:00 captured and circulated |
| Day risk | eTenders portal latency or attachment-size limits — pre-test upload by 14:00. |

# 6. Ten-skill execution matrix

Skills are sequenced by document availability and dependency. Mech skills run as a parallel batch on Day 4. Day-1 partial runs (arch-review, contract-admin) feed CRITICAL-item triage rather than full discipline registers.

| Skill | Day | Pack inputs | Primary authority corpus |
| --- | --- | --- | --- |
| arch-review-ireland | 1, 2, 3 | Architectural drawings, spec, BCAR pack | TGD B Vol 2 (2024), TGD M, BS 8300-2:2018, BS 9991:2024, NDA Building for Everyone, Changing Places, HBN/HTM, HIQA |
| cs-review-ireland | 2, 3 | Structural drawings, calcs, BCAR pack | Eurocodes + Irish NAs, I.S. EN 13670/1090/206, TGD A/C/D/H, GDSDS, TII Spec, SI 9/2014 |
| ee-review-ireland | 5 | Electrical pack, single-lines, lighting, alarm | I.S. 10101:2020, I.S. 3217:2023, I.S. 3218:2024, BS 8300-2 §18.6, HTM 06-01/02/08-03, CIBSE LG7/LG10 |
| mech-review (HVAC) | 4 | HVAC spec, BoQ, plant schedule | TGD L, CIBSE, F-Gas EU 2024/573 |
| mech-review (plumbing/drainage) | 4 | Plumbing/drainage spec, BoQ | TGD G, TGD H, I.S. EN 12056 |
| mech-review (BMS/controls) | 4 | BMS interface schedule, controls narrative | TGD L, BSRIA |
| mech-review (fire/life-safety mech) | 4 | Smoke control, sprinkler/wet-riser spec | TGD B, BS 9999, BS 9251 |
| mech-review (medical-gas if applicable) | 4 | MGPS spec (if scoped) | HTM 02-01 |
| qs-review-cwmf-ireland | 6 | FTS, ITT, FOT, MF, BoQ | CWMF ARM4 + Supp1Iss2, CESMM4 Revised, TII RMP, CE-17, Clause 15 PV, SI 284/2016 |
| contract-admin-pwcf-ireland | 1, 2, 7 | PW-CF docs, BCAR appointments, schedule of preconditions | PW-CF1/3/5 lifecycle, Construction Contracts Act 2013, SI 284/2016, BCAR SI 9/2014 |

# 7. Definition of Done — per finding

Every finding logged to the master register must satisfy every field below before it can be tagged Closed. Findings that cannot satisfy regulatory_basis or evidence_quote are demoted from CRITICAL/HIGH to MEDIUM pending substantiation.

| Field | Required content |
| --- | --- |
| finding_id | Discipline-prefixed unique ID — A-001, S-001, M-001, E-001, Q-001, C-001 |
| severity | CRITICAL · HIGH · MEDIUM · LOW (taxonomy aligned across all 10 skills) |
| category | Compliance · Cost · Programme · Contract · Document hygiene · Operational |
| document | Source document name + version |
| section | Specific clause / sheet / sub-section reference |
| regulatory_basis | Citation of the authority breached or at risk (e.g. SI 9/2014 Reg 5, TGD B 2.3.1) |
| operational_risk | One-line impact statement — what happens if not corrected before tender issue |
| recommended_action | Specific corrective text or action — drafted, not described |
| evidence_quote | Verbatim quote from source document supporting the finding |
| rfi_id | Mapped RFI / internal change request number (if RFI-eligible) |
| variation_exposure_€ | Quantified € exposure (or banded range) if unresolved at award |
| owner | Single accountable party — Employer / ER / Designer (named) / Contractor |
| status | Open · Stakeholder review · Accepted · Rejected · Deferred · Closed |

# 8. RFI register protocol

RFI register is generated from the master discrepancy register on Day 7, refined on Day 8 with stakeholder input, finalised on Day 9, submitted on Day 10.

- Numbering: RFI-001 onwards, contiguous, no gaps.

- Each RFI carries a back-reference to its source finding(s) by finding_id.

- RFI text: question to CA / Employer phrased as a closed clarification or a proposed change, not an open commentary.

- Each RFI states the proposed correction — never just identifies the issue.

- Severity propagates from the highest-severity source finding.

- Submission route confirmed on Day 1: eTenders portal (post-issue) or Employer document control (pre-issue).

- Submission must include timestamped evidence of receipt.

# 9. Variation exposure quantification model

Live model maintained Days 4–7, updated each time a CRITICAL or HIGH finding is added or revised. Roll-up published Day 7 and again Day 9 after stakeholder amendments.

- Each CRITICAL / HIGH finding tagged with €-exposure if unresolved at award — banded low / central / high.

- Bands derived from CWMF variation typology, CESMM4 measurement assumptions, and prevailing CRC sector unit rates.

- Total exposure reported as range (low total · central total · high total) rather than single point.

- If total exceeds €270k upper bound, escalate same day — triggers Employer cost-report re-scope conversation.

- Exposure model is the QS sign-off artefact — owns the commercial impact narrative for the Employer board.

# 10. 14-item Pre-Contract Action Checklist — sequencing model

Built on Day 7, sequenced Employer → ER → Designers → Contractor. Populated from cross-discipline findings; each item is a discrete pre-contract precondition mapped to one or more findings.

- Employer: confirm legal entity identity and align across FTS, ITT, FOT, Conditions of Contract, BCAR appointments (closes C-01).

- Employer: confirm BCAR delivery model — PW-CF5 Employer-Designed scope vs prior D&B drafting; instruct re-issue if required (closes C-02).

- Employer: confirm Date for Substantial Completion and LD rate; instruct insertion into Schedule Part 1 (closes C-03).

- Employer: confirm hoist brand selection (commercial / clinical preference) — closes brand conflict.

- Employer: confirm DAC / FSC status per discipline.

- ER: issue revised BCAR Ancillary Cert list aligned to confirmed delivery model.

- ER: issue revised FOT Schedule Part 1 with all blank fields populated.

- ER: issue corrected Irish standards citations (IS EN 10101 and similar).

- Designers: issue revised M&E pricing with correct project address and single-source hoist spec.

- Designers: issue cause-and-effect matrix (or scope brief for tenderer submission).

- Designers: reconcile contradictory car-park scope statements between drawings and spec.

- Designers: confirm F-Gas compliance under EU 2024/573 for refrigerant-bearing plant.

- Contractor (post-LoA): confirm preconditions checklist completion before Commencement Notice.

- Contractor (post-LoA): confirm Construction Contracts Act 2013 payment provisions adopted.

# 11. Risk register

Likelihood × Impact scored L / M / H. Only sprint-execution risks listed — project-execution risks captured separately in the master discrepancy register's operational_risk fields.

| # | Risk | L × I | Mitigation |
| --- | --- | --- | --- |
| R1 | Irish June Bank Holiday (Mon 1-Jun) consumes a working day inside the sprint window | H × M | Sprint built around 10 working days, not 11; no recovery slack until Day 9 amendment cut-off |
| R2 | Solo orchestrator single-point-of-failure (illness, system outage, family event) | L × H | Day-1 hand-over brief stored in project folder; CA pre-warned of sole-driver model; secondary reviewer on standby contract |
| R3 | RFI direction ambiguity (pre-issue internal change vs post-issue bidder RFI) not resolved Day 1 | M × H | Day-1 Activity 1 hard gate; if not resolved by 12:00 Day 2, escalate to CA / Employer in writing |
| R4 | Stakeholder turnaround latency on Day 8–9 compresses QA window | H × H | Issue Day-8 pack with explicit 24h response SLA; pre-book CA review slot Day 8 AM; hold 13:00 hard cut-off Day 9 |
| R5 | AI skill output variance — false negatives missed, false positives over-flagged | M × M | Spot-check protocol: every CRITICAL/HIGH validated against source text; LOW-tier accepted on sampling basis only |
| R6 | Variation exposure exceeds €270k upper bound, triggering cost-report re-scope | M × M | Live exposure model updated daily Days 4–7; Employer notified same day if upper bound exceeded |
| R7 | C-02 BCAR/PW-CF5 mismatch may require full BCAR re-issue — schedule extends past sprint | M × H | Day-2 deep dive produces decision paper; if re-issue required, sprint exit becomes 'BCAR re-issue scope agreed' rather than 'pack issued' |
| R8 | Hoist brand conflict (CARBITAN / ARJO / SEA) blocked on Employer commercial decision | M × M | Escalate Day 4; if no decision by Day 6, log as outstanding RFI with default specification |
| R9 | Tender pack missing supporting docs (FSC, DAC, F-Gas register) | M × M | Day-1 manifest exposes gaps; chase via CA same day |
| R10 | eTenders portal latency / attachment limits at 17:00 cut-off | L × H | Pre-test upload by 14:00 Day 10; backup submission via CA email with timestamp |

# 12. Sprint Exit Checklist — Day 10

Every item below must be a Yes before submission. A No on any item triggers either same-day correction or formal deferral with CA sign-off.

- All 3 CRITICAL findings closed (resolved, escalated, or formally deferred with CA sign-off)

- All 18 HIGH findings have a logged decision (accepted / rejected / deferred) with owner

- MEDIUM and LOW findings logged in master register with severity tag and recommended action

- 30-item RFI register finalised, numbered, mapped back to findings, formatted for submission route

- 14-item Pre-Contract Action Checklist sequenced Employer → ER → Designers → Contractor with named owners and target dates

- Variation exposure model finalised — total €-range circulated and acknowledged by CA / Employer

- FOT Schedule Part 1 redline complete — every blank field populated or formally flagged

- Standards-citation correction log applied (IS EN 10101 and similar errors swept)

- BCAR Ancillary Cert list aligned to PW-CF5 Employer-Designed scope (resolution of C-02)

- Date for Substantial Completion populated with defensible date and LD rate (resolution of C-03)

- Employer / CA / Building Owner identity confirmed and consistently used across all docs (resolution of C-01)

- F-Gas declaration confirmed for refrigerant-bearing plant under EU 2024/573

- Cause-and-effect matrix requirement issued to tenderers (or populated in pack)

- DAC / FSC status confirmed and stated per discipline

- Submission confirmed via eTenders (or pack issue confirmed via procurement route) with timestamped evidence before 17:00 Day 10

# 13. Sprint cadence

- Daily: 09:00 stand-up note logged to project folder — yesterday closed, today's gate, blockers. 17:00 EOD register push to findings store.

- Day 2 & Day 7: hard-gate review — sprint continues only if gate is met or formally deferred.

- Day 8 review session with CA / Employer / ER — minimum 2 hours, agenda mapped to CRITICAL → HIGH → MEDIUM → LOW.

- Day 10: 30-min retrospective — capture what to bake into the next pack-review sprint.

# 14. Tooling

- Findings store: Convex schema mirroring the 10-skill JSON output (review_metadata, findings[], rfi_register, summary_counts).

- Document control: project folder under '57 Rathbeale Road Design Review' — version every output Pack vN.M.

- Variation exposure model: linked spreadsheet, single source of truth for €-numbers.

- Sprint tracker: TaskCreate / TaskUpdate task list referenced from this plan; 1:1 with Phase gates.

- Submission route: eTenders portal or Employer procurement route — locked Day 1.