## Cover
57 Rathbeale Road
CRC Omni Unit 48A — Stage 2C Pack Manifest
Day 1 inventory · Issued 27-May-2026 · GovIQ
Top-line
Total files reviewed | 161
Total size (MB) | 128.4
Architectural files | 98
Civil & Structural files | 29
Mechanical files | 0
Electrical files | 33
M&E general files | 0
Fire (Appendix E) files | 1
Scope reality check
This pack is the Stage 2C design + reports issue — the technical content that will be bundled into the eventual tender pack.
The pack does NOT contain the contract documentation set (ITT, FOT, MF, FTS Notice, Conditions of Contract).
The pack does NOT contain the BCAR Ancillary Cert pack or BCAR appointment documents.
The pack does NOT contain the BoQ, Cost Plan or QS Pricing Document.
The pack does NOT contain DAC / FSC certificates, Disability Access certs, or PSDP Preliminary H&S Plan.
Appendix D is absent from the index sequence (A, B, C, E) — confirm what was assigned to D and whether it is required.
Consequence: arch / C&S / M&E / EE / fire reviews can proceed against this pack; QS-CWMF and contract-admin reviews are blocked pending the contract document set.
The 3 CRITICALs from the project brief (party identity / BCAR-PW-CF5 alignment / blank Substantial Completion date) cannot be evidenced from this pack — they live in the contract documentation that has not yet been supplied.

## Inventory
# | Appendix | Discipline | Doc Type | Drawing No. | Title | Filename | Size (MB) | Path
1 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-XXX-DR-RHA-AR-10001 | Site Location Map | 11606-XX-XXX-DR-RHA-AR-10001- Site Location Map.pdf | 0.31 | Appendix A - Architectural/Drawings/10000_Site Drawings/11606-XX-XXX-DR-RHA-AR-10001- Site Location Map.pdf
2 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-XXX-DR-RHA-AR-10002 | Site Survey & Site Demolition Plan | 11606-XX-XXX-DR-RHA-AR-10002- Site Survey & Site Demolition Plan.pdf | 0.87 | Appendix A - Architectural/Drawings/10000_Site Drawings/11606-XX-XXX-DR-RHA-AR-10002- Site Survey & Site Demolition Plan.pdf
3 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-XXX-DR-RHA-AR-10003 | Site Setup Plan | 11606-XX-XXX-DR-RHA-AR-10003- Site Setup Plan.pdf | 0.68 | Appendix A - Architectural/Drawings/10000_Site Drawings/11606-XX-XXX-DR-RHA-AR-10003- Site Setup Plan.pdf
4 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-11001 | GA Plan - Ground Floor | 11606-XX-L00-DR-RHA-AR-11001- GA Plan - Ground Floor.pdf | 2.72 | Appendix A - Architectural/Drawings/11000_GA Plans/11606-XX-L00-DR-RHA-AR-11001- GA Plan - Ground Floor.pdf
5 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-11002 | GA Plan - Roof Plan | 11606-XX-ZZZ-DR-RHA-AR-11002- GA Plan - Roof Plan.pdf | 2.05 | Appendix A - Architectural/Drawings/11000_GA Plans/11606-XX-ZZZ-DR-RHA-AR-11002- GA Plan - Roof Plan.pdf
6 | Appendix A - Architectural | ARCHITECTURAL | DRAWING REGISTER | 11606 | Drawing Register | 11606-RG-RHA-AR-0001 - Drawing Register.pdf | 0.74 | Appendix A - Architectural/Drawings/11606-RG-RHA-AR-0001 - Drawing Register.pdf
7 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-42-L00-DR-RHA-AR-13001 | Wall Finishes | 11606-42-L00-DR-RHA-AR-13001- Wall Finishes.pdf | 0.51 | Appendix A - Architectural/Drawings/13000_Internal Finishes Plans/11606-42-L00-DR-RHA-AR-13001- Wall Finishes.pdf
8 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-43-L00-DR-RHA-AR-13002 | Floor Finishes | 11606-43-L00-DR-RHA-AR-13002- Floor Finishes.pdf | 0.67 | Appendix A - Architectural/Drawings/13000_Internal Finishes Plans/11606-43-L00-DR-RHA-AR-13002- Floor Finishes.pdf
9 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-41-L00-DR-RHA-AR-15001 | Wall & Partition types | 11606-41-L00-DR-RHA-AR-15001- Wall & Partition types.pdf | 1.35 | Appendix A - Architectural/Drawings/15000_Wall and Partition Plans/11606-41-L00-DR-RHA-AR-15001- Wall & Partition types.pdf
10 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-17001 | Signage - Ground Floor | 11606-XX-ZZZ-DR-RHA-AR-17001- Signage - Ground Floor.pdf | 1.03 | Appendix A - Architectural/Drawings/17000_Signage Plans/11606-XX-ZZZ-DR-RHA-AR-17001- Signage - Ground Floor.pdf
11 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-17002 | Signage - Sheet 1 | 11606-XX-ZZZ-DR-RHA-AR-17002- Signage - Sheet 1.pdf | 1.03 | Appendix A - Architectural/Drawings/17000_Signage Plans/11606-XX-ZZZ-DR-RHA-AR-17002- Signage - Sheet 1.pdf
12 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-XXX-DR-RHA-AR-20001 | Elevations | 11606-XX-XXX-DR-RHA-AR-20001- Elevations.pdf | 3 | Appendix A - Architectural/Drawings/20000_GA Elevations/11606-XX-XXX-DR-RHA-AR-20001- Elevations.pdf
13 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-XXX-DR-RHA-AR-20002 | Courtyard 1 & 2 Elevations | 11606-XX-XXX-DR-RHA-AR-20002- Courtyard 1 & 2 Elevations.pdf | 2.63 | Appendix A - Architectural/Drawings/20000_GA Elevations/11606-XX-XXX-DR-RHA-AR-20002- Courtyard 1 & 2 Elevations.pdf
14 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-XXX-DR-RHA-AR-20003 | Courtyard 3 Elevations | 11606-XX-XXX-DR-RHA-AR-20003- Courtyard 3 Elevations.pdf | 2.95 | Appendix A - Architectural/Drawings/20000_GA Elevations/11606-XX-XXX-DR-RHA-AR-20003- Courtyard 3 Elevations.pdf
15 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-44-L00-DR-RHA-AR-25001 | Stair Layout - Floor Plan | 11606-44-L00-DR-RHA-AR-25001- Stair Layout - Floor Plan.pdf | 0.86 | Appendix A - Architectural/Drawings/25000_Stair Layout/11606-44-L00-DR-RHA-AR-25001- Stair Layout - Floor Plan.pdf
16 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-44-ZZZ-DR-RHA-AR-25002 | Stair Layout - Section & Elevations | 11606-44-ZZZ-DR-RHA-AR-25002- Stair Layout - Section & Elevations.pdf | 0.44 | Appendix A - Architectural/Drawings/25000_Stair Layout/11606-44-ZZZ-DR-RHA-AR-25002- Stair Layout - Section & Elevations.pdf
17 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-30001 | Sections AA & BB | 11606-XX-ZZZ-DR-RHA-AR-30001- Sections AA & BB.pdf | 2.14 | Appendix A - Architectural/Drawings/30000_Sections/11606-XX-ZZZ-DR-RHA-AR-30001- Sections AA & BB.pdf
18 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-30002 | Sections CC, DD & EE | 11606-XX-ZZZ-DR-RHA-AR-30002- Sections CC, DD & EE.pdf | 2.09 | Appendix A - Architectural/Drawings/30000_Sections/11606-XX-ZZZ-DR-RHA-AR-30002- Sections CC, DD & EE.pdf
19 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606 | 11606-XX-XXX-RHA-DR-RHA-AR-31001 | 11606-XX-XXX-RHA-DR-RHA-AR-31001.pdf | 0.47 | Appendix A - Architectural/Drawings/31000_Assembly Sections/11606-XX-XXX-RHA-DR-RHA-AR-31001.pdf
20 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606 | 11606-XX-XXX-RHA-DR-RHA-AR-31002 | 11606-XX-XXX-RHA-DR-RHA-AR-31002.pdf | 0.46 | Appendix A - Architectural/Drawings/31000_Assembly Sections/11606-XX-XXX-RHA-DR-RHA-AR-31002.pdf
21 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606 | 11606-XX-XXX-RHA-DR-RHA-AR-31003 | 11606-XX-XXX-RHA-DR-RHA-AR-31003.pdf | 0.66 | Appendix A - Architectural/Drawings/31000_Assembly Sections/11606-XX-XXX-RHA-DR-RHA-AR-31003.pdf
22 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-45-ZZZ-SH-RHA-AR-40013 | Ceiling Access Panel Schedule | 11606-45-ZZZ-SH-RHA-AR-40013- Ceiling Access Panel Schedule.pdf | 0.2 | Appendix A - Architectural/Drawings/40000_Schedules/11606-45-ZZZ-SH-RHA-AR-40013- Ceiling Access Panel Schedule.pdf
23 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-L00-SH-RHA-AR-40010 | Ironmongery & Access Control Plan & Schedule | 11606-XX-L00-SH-RHA-AR-40010- Ironmongery & Access Control Plan & Schedule.pdf | 0.45 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-L00-SH-RHA-AR-40010- Ironmongery & Access Control Plan & Schedule.pdf
24 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-XXX-SH-RHA-AR-40001 | Internal Doors Type Elevations & Schedule | 11606-XX-XXX-SH-RHA-AR-40001- Internal Doors Type Elevations & Schedule.pdf | 0.24 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-XXX-SH-RHA-AR-40001- Internal Doors Type Elevations & Schedule.pdf
25 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-XXX-SH-RHA-AR-40002 | Windows & External Doors Type Elevations & Schedules | 11606-XX-XXX-SH-RHA-AR-40002- Windows & External Doors Type Elevations & Schedules.pdf | 1.59 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-XXX-SH-RHA-AR-40002- Windows & External Doors Type Elevations & Schedules.pdf
26 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-XXX-SH-RHA-AR-40003 | Curtain Walls Type Elevations & Schedule | 11606-XX-XXX-SH-RHA-AR-40003- Curtain Walls Type Elevations & Schedule.pdf | 1.59 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-XXX-SH-RHA-AR-40003- Curtain Walls Type Elevations & Schedule.pdf
27 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-XXX-SH-RHA-AR-40005 | Blind Schedule | 11606-XX-XXX-SH-RHA-AR-40005- Blind Schedule.pdf | 0.19 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-XXX-SH-RHA-AR-40005- Blind Schedule.pdf
28 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-DR-RHA-AR-40007 | IPS Panel Type & Schedule | 11606-XX-ZZZ-DR-RHA-AR-40007- IPS Panel Type & Schedule.pdf | 0.38 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-DR-RHA-AR-40007- IPS Panel Type & Schedule.pdf
29 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-SH-RHA-AR-40004 | External Gate Type & Schedule | 11606-XX-ZZZ-SH-RHA-AR-40004- External Gate Type & Schedule.pdf | 0.2 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-SH-RHA-AR-40004- External Gate Type & Schedule.pdf
30 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-SH-RHA-AR-40006 | Sanitary Schedules | 11606-XX-ZZZ-SH-RHA-AR-40006- Sanitary Schedules.pdf | 0.2 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-SH-RHA-AR-40006- Sanitary Schedules.pdf
31 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-SH-RHA-AR-40008 | Architectural FF&E Components - Totals | 11606-XX-ZZZ-SH-RHA-AR-40008- Architectural FF&E Components - Totals.pdf | 0.21 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-SH-RHA-AR-40008- Architectural FF&E Components - Totals.pdf
32 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-SH-RHA-AR-40009 | Internal Finishes Schedule | 11606-XX-ZZZ-SH-RHA-AR-40009- Internal Finishes Schedule.pdf | 0.21 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-SH-RHA-AR-40009- Internal Finishes Schedule.pdf
33 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-SH-RHA-AR-40011 | Internal Screen Schedule & Detail | 11606-XX-ZZZ-SH-RHA-AR-40011- Internal Screen Schedule & Detail.pdf | 0.89 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-SH-RHA-AR-40011- Internal Screen Schedule & Detail.pdf
34 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-SH-RHA-AR-40012 | Fire Shutter Screen Schedule & Detail | 11606-XX-ZZZ-SH-RHA-AR-40012- Fire Shutter Screen Schedule & Detail.pdf | 1.96 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-SH-RHA-AR-40012- Fire Shutter Screen Schedule & Detail.pdf
35 | Appendix A - Architectural | ARCHITECTURAL | SCHEDULE | 11606-XX-ZZZ-SH-RHA-AR-40014 | Internal Access Panel Schedule | 11606-XX-ZZZ-SH-RHA-AR-40014- Internal Access Panel Schedule.pdf | 0.2 | Appendix A - Architectural/Drawings/40000_Schedules/11606-XX-ZZZ-SH-RHA-AR-40014- Internal Access Panel Schedule.pdf
36 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-32-ZZZ-DR-RHA-AR-51003 | Construction Details - Partitions - Sheet 1 | 11606-32-ZZZ-DR-RHA-AR-51003- Construction Details - Partitions - Sheet 1.pdf | 0.35 | Appendix A - Architectural/Drawings/50000_Details/11606-32-ZZZ-DR-RHA-AR-51003- Construction Details - Partitions - Sheet 1.pdf
37 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-32-ZZZ-DR-RHA-AR-51004 | Construction Details - Partitions - Sheet 2 | 11606-32-ZZZ-DR-RHA-AR-51004- Construction Details - Partitions - Sheet 2.pdf | 0.57 | Appendix A - Architectural/Drawings/50000_Details/11606-32-ZZZ-DR-RHA-AR-51004- Construction Details - Partitions - Sheet 2.pdf
38 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-43-ZZZ-DR-RHA-AR-51002 | Construction Details - Skirtings | 11606-43-ZZZ-DR-RHA-AR-51002- Construction Details - Skirtings.pdf | 0.22 | Appendix A - Architectural/Drawings/50000_Details/11606-43-ZZZ-DR-RHA-AR-51002- Construction Details - Skirtings.pdf
39 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-45-ZZZ-DR-RHA-AR-55001 | Construction Details - Ceilings | 11606-45-ZZZ-DR-RHA-AR-55001- Construction Details - Ceilings.pdf | 0.24 | Appendix A - Architectural/Drawings/50000_Details/11606-45-ZZZ-DR-RHA-AR-55001- Construction Details - Ceilings.pdf
40 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-72-XXX-DR-RHA-AR-57001 | Furniture Details - Front Foyer Seat | 11606-72-XXX-DR-RHA-AR-57001- Furniture Details - Front Foyer Seat.pdf | 0.66 | Appendix A - Architectural/Drawings/50000_Details/11606-72-XXX-DR-RHA-AR-57001- Furniture Details - Front Foyer Seat.pdf
41 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-72-XXX-DR-RHA-AR-57002 | Furniture Details - Entrance Foyer Seat 2 | 11606-72-XXX-DR-RHA-AR-57002- Furniture Details - Entrance Foyer Seat 2.pdf | 1.16 | Appendix A - Architectural/Drawings/50000_Details/11606-72-XXX-DR-RHA-AR-57002- Furniture Details - Entrance Foyer Seat 2.pdf
42 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-72-XXX-DR-RHA-AR-57003 | Furniture Details - Corridor Seat | 11606-72-XXX-DR-RHA-AR-57003- Furniture Details - Corridor Seat.pdf | 0.86 | Appendix A - Architectural/Drawings/50000_Details/11606-72-XXX-DR-RHA-AR-57003- Furniture Details - Corridor Seat.pdf
43 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-72-XXX-DR-RHA-AR-57004 | Furniture Details - Breakout Room Seat | 11606-72-XXX-DR-RHA-AR-57004- Furniture Details - Breakout Room Seat.pdf | 0.66 | Appendix A - Architectural/Drawings/50000_Details/11606-72-XXX-DR-RHA-AR-57004- Furniture Details - Breakout Room Seat.pdf
44 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-72-XXX-DR-RHA-AR-57005 | Furniture Details - Front Lobby Seat | 11606-72-XXX-DR-RHA-AR-57005- Furniture Details - Front Lobby Seat.pdf | 0.39 | Appendix A - Architectural/Drawings/50000_Details/11606-72-XXX-DR-RHA-AR-57005- Furniture Details - Front Lobby Seat.pdf
45 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-73-XXX-DR-RHA-AR-57011 | Staff Rest Layout - Room 0.19 | 11606-73-XXX-DR-RHA-AR-57011- Staff Rest Layout - Room 0.19.pdf | 0.67 | Appendix A - Architectural/Drawings/50000_Details/11606-73-XXX-DR-RHA-AR-57011- Staff Rest Layout - Room 0.19.pdf
46 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-73-XXX-DR-RHA-AR-57013 | Kitchennette Layout - Room 0.39 | 11606-73-XXX-DR-RHA-AR-57013- Kitchennette Layout - Room 0.39.pdf | 0.77 | Appendix A - Architectural/Drawings/50000_Details/11606-73-XXX-DR-RHA-AR-57013- Kitchennette Layout - Room 0.39.pdf
47 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-73-ZZZ-DR-RHA-AR-57012 | Kitchen Layout - Room 0.17 | 11606-73-ZZZ-DR-RHA-AR-57012- Kitchen Layout - Room 0.17.pdf | 0.6 | Appendix A - Architectural/Drawings/50000_Details/11606-73-ZZZ-DR-RHA-AR-57012- Kitchen Layout - Room 0.17.pdf
48 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-76-XXX-DR-RHA-AR-57006 | Furniture Details - 0.07 Gym Room | 11606-76-XXX-DR-RHA-AR-57006- Furniture Details - 0.07 Gym Room.pdf | 0.63 | Appendix A - Architectural/Drawings/50000_Details/11606-76-XXX-DR-RHA-AR-57006- Furniture Details - 0.07 Gym Room.pdf
49 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-76-XXX-DR-RHA-AR-57007 | Furniture Details - 0.15 Activity Room | 11606-76-XXX-DR-RHA-AR-57007- Furniture Details - 0.15 Activity Room.pdf | 0.69 | Appendix A - Architectural/Drawings/50000_Details/11606-76-XXX-DR-RHA-AR-57007- Furniture Details - 0.15 Activity Room.pdf
50 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-76-XXX-DR-RHA-AR-57008 | Furniture Details - 0.08 Group Therapy Room | 11606-76-XXX-DR-RHA-AR-57008- Furniture Details - 0.08 Group Therapy Room.pdf | 0.7 | Appendix A - Architectural/Drawings/50000_Details/11606-76-XXX-DR-RHA-AR-57008- Furniture Details - 0.08 Group Therapy Room.pdf
51 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-76-XXX-DR-RHA-AR-57009 | Furniture Details - 0.23, 0.24, 0.25, 0.26 & 0.28 Therapy Room | 11606-76-XXX-DR-RHA-AR-57009- Furniture Details - 0.23, 0.24, 0.25, 0.26 & 0.28 Therapy Room.pdf | 0.55 | Appendix A - Architectural/Drawings/50000_Details/11606-76-XXX-DR-RHA-AR-57009- Furniture Details - 0.23, 0.24, 0.25, 0.26 & 0.28 Therapy Room.pdf
52 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-76-XXX-DR-RHA-AR-57010 | Furniture Details - 0.34 Entrance Foyer Lockers | 11606-76-XXX-DR-RHA-AR-57010- Furniture Details - 0.34 Entrance Foyer Lockers.pdf | 0.44 | Appendix A - Architectural/Drawings/50000_Details/11606-76-XXX-DR-RHA-AR-57010- Furniture Details - 0.34 Entrance Foyer Lockers.pdf
53 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-53001 | Changing Room - Laid to Falls | 11606-XX-L00-DR-RHA-AR-53001- Changing Room - Laid to Falls.pdf | 0.24 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-L00-DR-RHA-AR-53001- Changing Room - Laid to Falls.pdf
54 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-53002 | Shower Room - Laid to Falls | 11606-XX-L00-DR-RHA-AR-53002- Shower Room - Laid to Falls.pdf | 0.24 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-L00-DR-RHA-AR-53002- Shower Room - Laid to Falls.pdf
55 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606 | 11606-XX-XXX-RHA-DR-RHA-AR-50001 | 11606-XX-XXX-RHA-DR-RHA-AR-50001.pdf | 0.48 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-XXX-RHA-DR-RHA-AR-50001.pdf
56 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606 | 11606-XX-XXX-RHA-DR-RHA-AR-50002 | 11606-XX-XXX-RHA-DR-RHA-AR-50002.pdf | 0.45 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-XXX-RHA-DR-RHA-AR-50002.pdf
57 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606 | 11606-XX-XXX-RHA-DR-RHA-AR-50003 | 11606-XX-XXX-RHA-DR-RHA-AR-50003.pdf | 0.64 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-XXX-RHA-DR-RHA-AR-50003.pdf
58 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606 | 11606-XX-XXX-RHA-DR-RHA-AR-50004 | 11606-XX-XXX-RHA-DR-RHA-AR-50004.pdf | 1.11 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-XXX-RHA-DR-RHA-AR-50004.pdf
59 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-59001 | Construction Details - Fire Stopping - Sheet 1 | 11606-XX-ZZZ-DR-RHA-AR-59001- Construction Details - Fire Stopping - Sheet 1.pdf | 0.28 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-ZZZ-DR-RHA-AR-59001- Construction Details - Fire Stopping - Sheet 1.pdf
60 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-59002 | Construction Details - Fire Stopping - Sheet 2 | 11606-XX-ZZZ-DR-RHA-AR-59002- Construction Details - Fire Stopping - Sheet 2.pdf | 0.26 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-ZZZ-DR-RHA-AR-59002- Construction Details - Fire Stopping - Sheet 2.pdf
61 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-59003 | Construction Details - Fire Stopping - Sheet 3 | 11606-XX-ZZZ-DR-RHA-AR-59003- Construction Details - Fire Stopping - Sheet 3.pdf | 0.24 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-ZZZ-DR-RHA-AR-59003- Construction Details - Fire Stopping - Sheet 3.pdf
62 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-ZZZ-DR-RHA-AR-59004 | Construction Details - Fire Stopping - Sheet 5 | 11606-XX-ZZZ-DR-RHA-AR-59004- Construction Details - Fire Stopping - Sheet 5.pdf | 0.45 | Appendix A - Architectural/Drawings/50000_Details/11606-XX-ZZZ-DR-RHA-AR-59004- Construction Details - Fire Stopping - Sheet 5.pdf
63 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-ZZ-ZZZ-DR-RHA-AR-51001 | Construction Details - Internal Door Junctions | 11606-ZZ-ZZZ-DR-RHA-AR-51001- Construction Details - Internal Door Junctions.pdf | 0.3 | Appendix A - Architectural/Drawings/50000_Details/11606-ZZ-ZZZ-DR-RHA-AR-51001- Construction Details - Internal Door Junctions.pdf
64 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 16060-37-ZZZ-DR-RHA-AR-52001 | Construction Details - Roof | 16060-37-ZZZ-DR-RHA-AR-52001- Construction Details - Roof.pdf | 1.52 | Appendix A - Architectural/Drawings/50000_Details/16060-37-ZZZ-DR-RHA-AR-52001- Construction Details - Roof.pdf
65 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60001 | 0.01 Staff Office | 11606-XX-L00-DR-RHA-AR-60001- 0.01 Staff Office.pdf | 0.54 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60001- 0.01 Staff Office.pdf
66 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60002 | 0.02 File & Comms | 11606-XX-L00-DR-RHA-AR-60002- 0.02 File & Comms.pdf | 0.43 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60002- 0.02 File & Comms.pdf
67 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60003 | 0.03 Cleaners Store | 11606-XX-L00-DR-RHA-AR-60003- 0.03 Cleaners Store.pdf | 0.5 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60003- 0.03 Cleaners Store.pdf
68 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60004 | 0.04 Staff Shower | 11606-XX-L00-DR-RHA-AR-60004- 0.04 Staff Shower.pdf | 0.47 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60004- 0.04 Staff Shower.pdf
69 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60005 | 0.05 Accessible WC | 11606-XX-L00-DR-RHA-AR-60005- 0.05 Accessible WC.pdf | 0.47 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60005- 0.05 Accessible WC.pdf
70 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60006 | 0.06 C-P WC | 11606-XX-L00-DR-RHA-AR-60006- 0.06 C-P WC.pdf | 0.51 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60006- 0.06 C-P WC.pdf
71 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60007 | 0.07 Gym | 11606-XX-L00-DR-RHA-AR-60007- 0.07 Gym.pdf | 0.53 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60007- 0.07 Gym.pdf
72 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60008 | 0.08 Group Therapy Room | 11606-XX-L00-DR-RHA-AR-60008- 0.08 Group Therapy Room.pdf | 0.5 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60008- 0.08 Group Therapy Room.pdf
73 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60009 | 0.09 Accessible WC | 11606-XX-L00-DR-RHA-AR-60009- 0.09 Accessible WC.pdf | 0.47 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60009- 0.09 Accessible WC.pdf
74 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60010 | 0.10 Sensory Room | 11606-XX-L00-DR-RHA-AR-60010- 0.10 Sensory Room.pdf | 0.42 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60010- 0.10 Sensory Room.pdf
75 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60011 | 0.11 Accessible WC | 11606-XX-L00-DR-RHA-AR-60011- 0.11 Accessible WC.pdf | 0.47 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60011- 0.11 Accessible WC.pdf
76 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60012 | 0.12 Therapy Room | 11606-XX-L00-DR-RHA-AR-60012- 0.12 Therapy Room.pdf | 0.42 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60012- 0.12 Therapy Room.pdf
77 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60013 | 0.13 Breakout Room | 11606-XX-L00-DR-RHA-AR-60013- 0.13 Breakout Room.pdf | 0.42 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60013- 0.13 Breakout Room.pdf
78 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60014 | 0.14 Store | 11606-XX-L00-DR-RHA-AR-60014- 0.14 Store.pdf | 0.41 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60014- 0.14 Store.pdf
79 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60015 | 0.15 Activity Room | 11606-XX-L00-DR-RHA-AR-60015- 0.15 Activity Room.pdf | 0.52 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60015- 0.15 Activity Room.pdf
80 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60016 | 0.16 Dining Hall | 11606-XX-L00-DR-RHA-AR-60016- 0.16 Dining Hall.pdf | 0.59 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60016- 0.16 Dining Hall.pdf
81 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60017 | 0.17 Kitchen | 11606-XX-L00-DR-RHA-AR-60017- 0.17 Kitchen.pdf | 0.55 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60017- 0.17 Kitchen.pdf
82 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60018 | 0.18 Manager's Office | 11606-XX-L00-DR-RHA-AR-60018- 0.18 Manager's Office.pdf | 0.59 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60018- 0.18 Manager's Office.pdf
83 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60019 | 0.19 Staff Rest | 11606-XX-L00-DR-RHA-AR-60019- 0.19 Staff Rest.pdf | 0.64 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60019- 0.19 Staff Rest.pdf
84 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60020 | 0.20 Activity Room & Kitchennette | 11606-XX-L00-DR-RHA-AR-60020- 0.20 Activity Room & Kitchennette.pdf | 0.55 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60020- 0.20 Activity Room & Kitchennette.pdf
85 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60021 | 0.21 Store | 11606-XX-L00-DR-RHA-AR-60021- 0.21 Store.pdf | 0.41 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60021- 0.21 Store.pdf
86 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60022 | 0.22 Accessibility WC | 11606-XX-L00-DR-RHA-AR-60022- 0.22 Accessibility WC.pdf | 0.47 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60022- 0.22 Accessibility WC.pdf
87 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60023 | 0.23 Therapy Room | 11606-XX-L00-DR-RHA-AR-60023- 0.23 Therapy Room.pdf | 0.44 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60023- 0.23 Therapy Room.pdf
88 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60024 | 0.24 Therapy Room | 11606-XX-L00-DR-RHA-AR-60024- 0.24 Therapy Room.pdf | 0.43 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60024- 0.24 Therapy Room.pdf
89 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60025 | 0.25 Therapy Room | 11606-XX-L00-DR-RHA-AR-60025- 0.25 Therapy Room.pdf | 0.43 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60025- 0.25 Therapy Room.pdf
90 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60026 | 0.26 Therapy Room | 11606-XX-L00-DR-RHA-AR-60026- 0.26 Therapy Room.pdf | 0.43 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60026- 0.26 Therapy Room.pdf
91 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60027 | 0.27 Sensory Room | 11606-XX-L00-DR-RHA-AR-60027- 0.27 Sensory Room.pdf | 0.42 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60027- 0.27 Sensory Room.pdf
92 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60028 | 0.28 Therapy Room | 11606-XX-L00-DR-RHA-AR-60028- 0.28 Therapy Room.pdf | 0.43 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60028- 0.28 Therapy Room.pdf
93 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60029 | 0.29 Accessible WC | 11606-XX-L00-DR-RHA-AR-60029- 0.29 Accessible WC.pdf | 0.46 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60029- 0.29 Accessible WC.pdf
94 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60030 | 0.30 Accessible WC | 11606-XX-L00-DR-RHA-AR-60030- 0.30 Accessible WC.pdf | 0.47 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60030- 0.30 Accessible WC.pdf
95 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60031 | 0.31 Plant Room | 11606-XX-L00-DR-RHA-AR-60031- 0.31 Plant Room.pdf | 0.47 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60031- 0.31 Plant Room.pdf
96 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-XX-L00-DR-RHA-AR-60032 | 0.32 Meeting & Consulation | 11606-XX-L00-DR-RHA-AR-60032- 0.32 Meeting & Consulation.pdf | 0.49 | Appendix A - Architectural/Drawings/60000_Room Layout Sheets/11606-XX-L00-DR-RHA-AR-60032- 0.32 Meeting & Consulation.pdf
97 | Appendix A - Architectural | ARCHITECTURAL | DRAWING | 11606-45-L00-DR-RHA-AR-70001 | Reflected Ceiling Plan | 11606-45-L00-DR-RHA-AR-70001- Reflected Ceiling Plan.pdf | 0.52 | Appendix A - Architectural/Drawings/70000_RCP/11606-45-L00-DR-RHA-AR-70001- Reflected Ceiling Plan.pdf
98 | Appendix A - Architectural | ARCHITECTURAL | SPECIFICATION | 11606-ZZ-ZZZ-SP-RHA-AR-91011 | Architectural Works Specification | 11606-ZZ-ZZZ-SP-RHA-AR-91011 Architectural Works Specification.pdf | 2.27 | Appendix A - Architectural/Specification/11606-ZZ-ZZZ-SP-RHA-AR-91011 Architectural Works Specification.pdf
99 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 11001 | FOUNDATION PLAN | 11001 - FOUNDATION PLAN.pdf | 0.76 | Appendix B - Civil and Structural/PDF DRAWINGS/11001 - FOUNDATION PLAN.pdf
100 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 11002 | GROUND FLOOR PLAN | 11002 - GROUND FLOOR PLAN.pdf | 1.36 | Appendix B - Civil and Structural/PDF DRAWINGS/11002 - GROUND FLOOR PLAN.pdf
101 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 11003 | ROOF PLAN | 11003 - ROOF PLAN.pdf | 0.69 | Appendix B - Civil and Structural/PDF DRAWINGS/11003 - ROOF PLAN.pdf
102 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 12001 | PROPOSED DRAINAGE | 12001 - PROPOSED DRAINAGE.pdf | 1.19 | Appendix B - Civil and Structural/PDF DRAWINGS/12001 - PROPOSED DRAINAGE.pdf
103 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 12002 | PROPOSED DRAINAGE - Sections | 12002 - PROPOSED DRAINAGE - Sections.pdf | 0.09 | Appendix B - Civil and Structural/PDF DRAWINGS/12002 - PROPOSED DRAINAGE - Sections.pdf
104 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 12003 | PAVING AREAS & GREEN ROOF | 12003 - PAVING AREAS & GREEN ROOF.pdf | 1.02 | Appendix B - Civil and Structural/PDF DRAWINGS/12003 - PAVING AREAS & GREEN ROOF.pdf
105 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 12004 | Surface Water Extension | 12004 - Surface Water Extension.pdf | 0.13 | Appendix B - Civil and Structural/PDF DRAWINGS/12004 - Surface Water Extension.pdf
106 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 12005 | PROPOSED DRAINAGE TYPICAL DETAILS | 12005 - PROPOSED DRAINAGE TYPICAL DETAILS.pdf | 0.13 | Appendix B - Civil and Structural/PDF DRAWINGS/12005 - PROPOSED DRAINAGE TYPICAL DETAILS.pdf
107 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50001 | 1-8 m Boundary wall details | 50001 - 1-8 m Boundary wall details.pdf | 1.1 | Appendix B - Civil and Structural/PDF DRAWINGS/50001 - 1-8 m Boundary wall details.pdf
108 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50002 | Rear Retaining Wall | 50002 - Rear Retaining Wall.pdf | 0.74 | Appendix B - Civil and Structural/PDF DRAWINGS/50002 - Rear Retaining Wall.pdf
109 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50003 | Parapet & Canopy Details | 50003 - Parapet & Canopy Details.pdf | 0.31 | Appendix B - Civil and Structural/PDF DRAWINGS/50003 - Parapet & Canopy Details.pdf
110 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50004 | RC Roof slab | 50004 - RC Roof slab.pdf | 1.57 | Appendix B - Civil and Structural/PDF DRAWINGS/50004 - RC Roof slab.pdf
111 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50005 | RC Walls (Typical) | 50005 - RC Walls (Typical).pdf | 0.61 | Appendix B - Civil and Structural/PDF DRAWINGS/50005 - RC Walls (Typical).pdf
112 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50007 | External Stair | 50007 - External Stair.pdf | 0.31 | Appendix B - Civil and Structural/PDF DRAWINGS/50007 - External Stair.pdf
113 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50008 | General Openings | 50008 - General Openings.pdf | 0.65 | Appendix B - Civil and Structural/PDF DRAWINGS/50008 - General Openings.pdf
114 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING | 50009 | STRUCTURE FOR CANOPY | 50009 - STRUCTURE FOR CANOPY.pdf | 0.22 | Appendix B - Civil and Structural/PDF DRAWINGS/50009 - STRUCTURE FOR CANOPY.pdf
115 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING REGISTER |  | DR01 - DRAWINGS REGISTER | DR01 - DRAWINGS REGISTER.pdf | 0.07 | Appendix B - Civil and Structural/PDF DRAWINGS/DR01 - DRAWINGS REGISTER.pdf
116 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0000 - RC KEYPLAN | RC0000 - RC KEYPLAN.pdf | 0.71 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0000 - RC KEYPLAN.pdf
117 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0001 - RC SHEET 01 | RC0001 - RC SHEET 01.pdf | 0.3 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0001 - RC SHEET 01.pdf
118 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0001 - RC SHEET 02 | RC0001 - RC SHEET 02.pdf | 0.29 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0001 - RC SHEET 02.pdf
119 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0001 - RC SHEET 03 | RC0001 - RC SHEET 03.pdf | 0.33 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0001 - RC SHEET 03.pdf
120 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0001 - RC SHEET 04 | RC0001 - RC SHEET 04.pdf | 0.32 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0001 - RC SHEET 04.pdf
121 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0001 - RC SHEET 05 | RC0001 - RC SHEET 05.pdf | 0.28 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0001 - RC SHEET 05.pdf
122 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0001 - RC SHEET 06 | RC0001 - RC SHEET 06.pdf | 0.32 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0001 - RC SHEET 06.pdf
123 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | DRAWING |  | RC0001 - RC SHEET 07 | RC0001 - RC SHEET 07.pdf | 0.33 | Appendix B - Civil and Structural/PDF DRAWINGS/RC0001 - RC SHEET 07.pdf
124 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | SCHEDULE / CALC |  | Bending_Schedule | Bending_Schedule.xlsx | 0.04 | Appendix B - Civil and Structural/SCHEDULES/Bending_Schedule.xlsx
125 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | SCHEDULE / CALC |  | Cl 2309 - SurfaceWaterAttenuation | Cl 2309 - SurfaceWaterAttenuation.xlsx | 0.04 | Appendix B - Civil and Structural/SCHEDULES/Cl 2309 - SurfaceWaterAttenuation.xlsx
126 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | SCHEDULE / CALC |  | Foundation Sheets Mesh Calculator | Foundation Sheets Mesh Calculator.xlsx | 0.04 | Appendix B - Civil and Structural/SCHEDULES/Foundation Sheets Mesh Calculator.xlsx
127 | Appendix B - Civil and Structural | CIVIL & STRUCTURAL | SPECIFICATION |  | Specifications - Rathbeale Rd | Specifications - Rathbeale Rd.pdf | 7.39 | Appendix B - Civil and Structural/SPECIFICATION/Specifications - Rathbeale Rd.pdf
128 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING REGISTER | 1743_Drgissue | rgissue 2C-Issue Sheet 1 of 3 | 1743_Drgissue 2C-Issue Sheet 1 of 3.pdf | 0.09 | Appendix C - Mechanical and Electrical/1743_Drgissue 2C-Issue Sheet 1 of 3.pdf
129 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING REGISTER | 1743_Drgissue | rgissue 2C-Issue Sheet 2 of 3 | 1743_Drgissue 2C-Issue Sheet 2 of 3.pdf | 0.09 | Appendix C - Mechanical and Electrical/1743_Drgissue 2C-Issue Sheet 2 of 3.pdf
130 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING REGISTER | 1743_Drgissue | rgissue 2C-Issue Sheet 3 of 3 | 1743_Drgissue 2C-Issue Sheet 3 of 3.pdf | 0.07 | Appendix C - Mechanical and Electrical/1743_Drgissue 2C-Issue Sheet 3 of 3.pdf
131 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_60_00 | 1743_60_00 | 1743_60_00.pdf | 1.24 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_60_00.pdf
132 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_60_01 | 1743_60_01 | 1743_60_01.pdf | 1.14 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_60_01.pdf
133 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_62_00 | 1743_62_00 | 1743_62_00.pdf | 1.22 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_62_00.pdf
134 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_62_01 | 1743_62_01 | 1743_62_01.pdf | 1.3 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_62_01.pdf
135 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_63-01 | 1743_63-01 | 1743_63-01.pdf | 1.33 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_63-01.pdf
136 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_63_00 | 1743_63_00 | 1743_63_00.pdf | 1.51 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_63_00.pdf
137 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_64_00 | 1743_64_00 | 1743_64_00.pdf | 1.21 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_64_00.pdf
138 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_65_BMS | Controls_00 | 1743_65_BMS Controls_00.pdf | 1.28 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_65_BMS Controls_00.pdf
139 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_65_BMS | Controls_01 | 1743_65_BMS Controls_01.pdf | 0.63 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_65_BMS Controls_01.pdf
140 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_68_00 | 1743_68_00 | 1743_68_00.pdf | 1.37 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_68_00.pdf
141 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_68_01 | 1743_68_01 | 1743_68_01.pdf | 1.22 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_68_01.pdf
142 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_69_00 | 1743_69_00 | 1743_69_00.pdf | 0.81 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_69_00.pdf
143 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_69_01 | 1743_69_01 | 1743_69_01.pdf | 0.74 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_69_01.pdf
144 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_69_02 | 1743_69_02 | 1743_69_02.pdf | 0.83 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_69_02.pdf
145 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_69_03 | 1743_69_03 | 1743_69_03.pdf | 0.63 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_69_03.pdf
146 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_69_04 | 1743_69_04 | 1743_69_04.pdf | 0.71 | Appendix C - Mechanical and Electrical/Electrical Drawings/1743_69_04.pdf
147 | Appendix C - Mechanical and Electrical | ELECTRICAL | SPECIFICATION |  | Electrical Specifiction | Electrical Specifiction .pdf | 1.19 | Appendix C - Mechanical and Electrical/Electrical Specifications/Electrical Specifiction .pdf
148 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_50_00 | 1743_50_00 | 1743_50_00.pdf | 1.08 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_50_00.pdf
149 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_52_00 | 1743_52_00 | 1743_52_00.pdf | 1.51 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_52_00.pdf
150 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_52_01 | 1743_52_01 | 1743_52_01.pdf | 0.62 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_52_01.pdf
151 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_53_00 | 1743_53_00 | 1743_53_00.pdf | 1.64 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_53_00.pdf
152 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_55_00 | 1743_55_00 | 1743_55_00.pdf | 1.28 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_55_00.pdf
153 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_55_01 | 1743_55_01 | 1743_55_01.pdf | 0.63 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_55_01.pdf
154 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_56_00 | 1743_56_00 | 1743_56_00.pdf | 1.66 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_56_00.pdf
155 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_56_01 | 1743_56_01 | 1743_56_01.pdf | 1.98 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_56_01.pdf
156 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_57_00 | 1743_57_00 | 1743_57_00.pdf | 1.68 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_57_00.pdf
157 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_57_01 | 1743_57_01 | 1743_57_01.pdf | 1.09 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_57_01.pdf
158 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_59_00 | 1743_59_00 | 1743_59_00.pdf | 0.98 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_59_00.pdf
159 | Appendix C - Mechanical and Electrical | ELECTRICAL | DRAWING | 1743_59_01 | 1743_59_01 | 1743_59_01.pdf | 1.04 | Appendix C - Mechanical and Electrical/Mechanical Drawings/1743_59_01.pdf
160 | Appendix C - Mechanical and Electrical | ELECTRICAL | SPECIFICATION |  | Mechanical Specification | Mechanical Specification.pdf | 1.69 | Appendix C - Mechanical and Electrical/Mechanical Specifications/Mechanical Specification.pdf
161 | Appendix E - Fire Consultant | FIRE | REPORT | 22481 | tage 2C Report-Part B Compliance | 22481-Stage 2C Report-Part B Compliance.pdf | 0.94 | Appendix E - Fire Consultant/22481-Stage 2C Report-Part B Compliance.pdf

## Gap Analysis
# | Required Document | Category | Required For | Status | Severity if Missing | Notes / Source
1 | Form of Tender (FOT) including Schedule Part 1 | Contract | PW-CF5 issue / contract-admin review | MISSING | CRITICAL | Required to evidence C-01 (party identity), C-03 (Substantial Completion date), Liquidated Damages rate
2 | Instructions to Tenderers (ITT) | Contract | QS / CWMF review, tenderer guidance | MISSING | CRITICAL | Required to evidence ITT date arithmetic finding from project brief
3 | FTS Notice / OJEU notice | Contract | Procurement compliance / SI 284/2016 | MISSING | HIGH | Required for procurement-route compliance check
4 | Conditions of Contract (PW-CF5) | Contract | Contract-admin review, LD enforceability | MISSING | CRITICAL | Base contract document — required for C-01, C-02, C-03 evidence
5 | Model Forms (MF) for PW-CF5 | Contract | Contract-admin review | MISSING | HIGH | Model Forms accompany PW-CF5
6 | Form of Letter of Acceptance (LoA) | Contract | Pre-contract checklist | MISSING | MEDIUM | Required for LoA-precondition mapping
7 | Bill of Quantities (BoQ) / Pricing Document | Commercial | QS / CWMF review, variation exposure | MISSING | CRITICAL | Blocks qs-review-cwmf-ireland entirely. ARM4/CESMM4 measurement check requires this.
8 | Cost Plan / Pre-Tender Estimate | Commercial | Variation exposure baseline | MISSING | HIGH | Without baseline, € exposure quantification is rate-based only
9 | Pricing Schedule / Schedule of Rates | Commercial | QS review, M&E pricing reconciliation | MISSING | HIGH | Project brief flagged M&E pricing references wrong project address — cannot evidence without this
10 | BCAR Form of Notice of Assignment | BCAR | Assigned Certifier role, SI 9/2014 | MISSING | CRITICAL | Closes C-02 part 1. Must be PW-CF5 Employer-Designed model — user confirmed 27-May-2026.
11 | BCAR Schedule of Designers (Ancillary Certs) | BCAR | Design responsibility allocation | MISSING | CRITICAL | Closes C-02 part 2. Must align to Employer-Designed model.
12 | BCAR Design Certifier appointment letter | BCAR | BCAR compliance | MISSING | HIGH | Required for SI 9/2014 Reg 9 compliance
13 | BCAR Preliminary Inspection Plan | BCAR | BCAR compliance | MISSING | MEDIUM
14 | Disability Access Certificate (DAC) — status | Cert | TGD M / BS 8300-2 compliance evidence | STATUS UNKNOWN | HIGH | Project brief flagged DAC status unstated. Confirm grant / pending / N/A.
15 | Fire Safety Certificate (FSC) — status | Cert | TGD B compliance evidence | STATUS UNKNOWN | HIGH | Project brief flagged FSC status unstated. Confirm grant / pending / N/A.
16 | F-Gas declaration / register (EU 2024/573) | Cert | Refrigerant compliance | MISSING | MEDIUM | Required for refrigerant-bearing plant under EU 2024/573
17 | PSDP appointment letter | Safety | S.I. 504/2006 compliance | MISSING | HIGH
18 | Preliminary H&S Plan | Safety | PSDP / pre-construction info | MISSING | HIGH
19 | Existing Safety File (if redevelopment) | Safety | Pre-existing condition info | MISSING | MEDIUM | Site survey indicates demolition — check if Safety File transfers
20 | Geotechnical / Ground Investigation Report | Survey | C&S design assumptions | MISSING | HIGH | Foundation plan present but underlying GI report not in pack
21 | Topographic Survey | Survey | Site geometry | PARTIAL | MEDIUM | Site Survey & Demolition Plan present; full topo survey not confirmed
22 | Utility Survey / Existing Services Survey | Survey | Drainage / utility coordination | MISSING | MEDIUM
23 | Existing Tree Survey / Arboricultural Report | Survey | Planning conditions | MISSING | LOW
24 | Appendix D — content unknown | Pack Structure | Gap in alphabetic index | MISSING (UNCONFIRMED) | HIGH | Index runs A, B, C, E — confirm what was assigned to Appendix D (DAC report? Drainage report? Hydrogeology?)
25 | Fire Alarm Cause-and-Effect Matrix | M&E | I.S. 3218:2024, BS 5839 | MISSING | HIGH | Project brief flagged absence. Either populate or require tenderer submission.
26 | Hoist Specification (single source) | M&E / Equipment | Brand conflict resolution | STATUS UNKNOWN | HIGH | Project brief flagged CARBITAN vs ARJO vs SEA conflict — confirm governing brand
27 | Architectural drawings & specification | Design | Arch review | PRESENT | — | Appendix A complete with drawing register
28 | C&S drawings + bending / mesh / attenuation schedules | Design | C&S review | PRESENT (PARTIAL) | — | Drawings + 3 schedules present. Calc package and ground investigation report not in pack.
29 | M&E drawings + Mech & Elec specs | Design | M&E review | PRESENT | — | Appendix C complete with drawing issue sheets
30 | Fire Part B Compliance Report (Appendix E) | Design | Fire / TGD B review | PRESENT | — | 22481-Stage 2C Report-Part B Compliance.pdf — 1 doc only

## By Discipline
Pack Summary by Discipline
Discipline | Drawings | Schedules | Specifications | Reports | Other | Total
ARCHITECTURAL | 82 | 14 | 1 | 0 | 0 | 98
CIVIL & STRUCTURAL | 24 | 3 | 1 | 0 | 0 | 29
ELECTRICAL | 28 | 0 | 2 | 0 | 0 | 33
FIRE | 0 | 0 | 0 | 1 | 0 | 1